## Gantt Chart
GANTT CHART - For Assignment 1 & 2 | [5 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | [Project's title] |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | [Project Manager's name] |  |  |  | DATE | [6 empty] | 2018-03-12
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Identify Data Set & Define Poblem
1.1 | Frame & Identify the Problem | Donald | 2020-04-28 | 2020-05-18 | 20 | bar: WEEK 1 M to WEEK 1 F
1.2 | Look for apporitate data set from public | Donald | 2020-05-10 | 2020-05-18 | 8 | bar: WEEK 2 M to WEEK 2 F
1.3 | Understand the data | Donald | 2020-05-10 | 2020-05-21 | 11 | bar: WEEK 2 M to WEEK 3 T
1.4 | Familiarity with data, | Donald | 2020-05-10 | 2020-05-21 | 11 | bar: WEEK 2 M to WEEK 3 T
1.5 | Merging datasets | Donald | 2020-05-10 | 2020-05-21 | 11 | bar: WEEK 2 M to WEEK 3 T
1.6 | Data Verfication & Identify Problem to Solve | Donald , Marta | 2020-05-21 | 2020-05-24 | 3 | bar: WEEK 3 W to WEEK 3 F
1.7 | Research current Problem | Donald | 2020-05-25 | 2020-05-29 | 4 | bar: WEEK 3 F to WEEK 4 W
1.8 | Planing apporach (methods, approach, algorithms, APIs) | Donald | 2020-05-25 | 2020-05-29 | 4 | bar: WEEK 3 F to WEEK 4 W
1.9 | Design & Planning : Analyse Data Set | Donald | 2020-05-29 | 2020-06-01 | 2 | bar: WEEK 4 R to WEEK 4 F
2 | Design & Planning : Clean DataSet | Donald | 2020-05-29 | 2020-06-01 | 2 | bar: WEEK 4 R to WEEK 4 F
2.1 | Design & Planning : Test & Stimulate DataSet | Donald | 2020-05-29 | 2020-06-01 | 2 | bar: WEEK 4 R to WEEK 4 F
2.2 | Design & Planning : Methodlogy implementaion | Donald | 2020-05-29 | 2020-06-01 | 2 | bar: WEEK 4 R to WEEK 4 F
2.3 | Assignment 1 Preparation & Kick Start | Donald | 2020-06-01 | 2020-06-13 | 12 | bar: WEEK 5 M to WEEK 7 W
2.4 | Assignment 1 Submission | Donald | 2020-06-13 | 2020-06-13 | 0 | bar: WEEK 7 R
2 | Project Execution for Assignment 2
2.1 | Build or Tune a detection Model | Donald | 2020-06-13 | 2020-06-15 | 2 | bar: WEEK 7 R to WEEK 7 F
2.2 | Analyse the date to find insight | Donald | 2020-06-15 | 2020-06-18 | 3 | bar: WEEK 8 M to WEEK 8 W
2.3 | Design and develop a SW to implement models | Donald | 2020-06-18 | 2020-07-06 | 18 | bar: WEEK 8 R to WEEK 11 W
2.4 | Test the model | Donald | 2020-06-18 | 2020-07-06 | 18 | bar: WEEK 8 R to WEEK 11 W
2.2 | Assignment 2 Preparation and Kick start | Donald | 2020-07-06 | 2020-07-15 | 9 | bar: WEEK 11 R to WEEK 12 F
2.3 | Machine Learning Method, Design and Web App implementation | Donald | 2020-07-06 | 2020-07-15 | 9 | bar: WEEK 11 R to WEEK 12 F
2.4 | Analyse the result | Donald | 2020-07-06 | 2020-07-15 | 9
2.2 | Complete Draft Assignment 2 | Donald | 2020-07-12 | 2020-07-12 | 0
2.3 | Review with Marta & Final Revision | Donald , Marta | 2020-07-15 | 2020-07-17 | 2
2.4 | Assignment 2 Submission | Donald | 2020-07-17 | 2020-07-17 | 0